## Work Order Tracking Form
Work Order Tracker
Work Order # | Description | Requested By | Assigned To | Start Date | Due Date | Done Date | % Complete | Status
1 | SDD - surfacemanager internal sequence | HQ | Trieu.phan | 16/9/2024 | 29/9/2024 | 23/9/2024 | 100% | 1
2 | SAD - requested review completed | HQ | Trieu.phan | 2024-05-09 | 13/9/2024 | 2024-10-09 | 100% | 1
3 | SDD - surfacemanager.extended internal sequence | HQ | Trieu.phan | 16/9/2024 | 29/9/2024 | 22/9/2024 | 100% | 1
4 | SDD - surfacemanager.input internal sequence | HQ | Trieu.phan | 16/9/2024 | 29/9/2024 | 24/9/2024 | 100% | 1
5 | Research features of LSM and architecture overview | Team lead | Trieu.phan | 25/9/2024 | 25/9/2024 |  | 50% | -1
6 | sysuicompmgr::launch sequence for the coming tasks | HQ | Trieu.phan | 26/9/2024 |  |  | 100% | 1
7 | Research onSurfaceRemoved | Team lead | Trieu.phan | 27/9/24 |  |  | 100% | 1
8 | X's button research | HQ | Trieu.phan | 26/9/2024 |  |  | 20%
9 | HMCCCRC-19439
10 | HMCCCRC-19419
N | Upgrade desktop computer | Person 2 | Person 3 | 2024-10-07 | 2024-11-06 |  | 0% | -1
Formulas:
Status = IFERROR(IF(WorkOrders[[#This Row],[% Complete]]=1,1,IF(ISBLANK(WorkOrders[[#This Row],[Due Date]]),"",IF(AND(TODAY()>WorkOrders[[#This Row],[Due Date]],WorkOrders[[#This Row],[% Complete]]<>1),0,-1))), "")
Due Date = WorkOrders[[#This Row],[Start Date]]+30